## Gantt Chart
ZIMSON SERVICE MANAGEMENT — PROJECT GANTT CHART
Project Period: Apr 2026 – Jun 2026 ¦ Generated: 13/5/2026 | [9 empty] | ■ Completed |  | ■ In Progress |  | ■ Planned
# | Task / Deliverable | Owner | % | W1 06/04 | W2 13/04 | W3 20/04 | W4 27/04 | W5 04/05 | W6 11/05 | W7 18/05 | W8 25/05 | W9 01/06 | W10 08/06 | W11 15/06 | W12 22/06
PHASE 1 — Core System Setup
1 | Project scaffold & DB schema | Full Stack | 100% | ◆
2 | Authentication & session mgmt | Backend | 100% | ◀ | ▶
3 | Sidebar & role-based routing | Frontend | 100% | ◀ | ▶
4 | Toast / notification system | Frontend | 100% |  | ◆
PHASE 2 — Master Data
5 | Region management + PIN lookup | Full Stack | 100% |  | ◀ | ▶
6 | Store & warehouse management | Full Stack | 100% |  |  | ◆
7 | User creation & role system | Full Stack | 100% |  |  | ◀ | ▶
8 | Demo login — DB users | Frontend | 100% |  |  |  | ◆
9 | Spares catalogue & bulk import | Full Stack | 100% |  |  |  | ◀ | ▶
PHASE 3 — Inventory Procurement
10 | Supplier master + spare mapping | Full Stack | 100% |  |  |  |  | ◀ | ▶
11 | Purchase Request (PR) creation | Full Stack | 100% |  |  |  |  | ◀ | ▶
12 | PR approval workflow | Full Stack | 100% | [5 empty] | ◆
13 | PR History page | Frontend | 100% | [5 empty] | ◀ | ▶
14 | Purchase Order (PO) creation | Full Stack | 100% | [6 empty] | ◆
15 | PO History page | Frontend | 100% | [6 empty] | ◆
PHASE 4 — Goods Receipt & Stock
16 | GRN — cost price & HSN tax | Full Stack | 100% | [6 empty] | ◀ | ▶
17 | GRN — vendor invoice upload | Full Stack | 100% | [7 empty] | ◆
18 | GRN History page | Frontend | 100% | [7 empty] | ◆
19 | PR auto-status from GRN | Backend | 100% | [7 empty] | ◆
20 | HO → Store stock fulfil | Full Stack | 100% | [7 empty] | ◀ | ▶
PHASE 5 — Notifications & Comms
21 | PR submission notifications | Backend | 100% | [5 empty] | ◆
22 | PR approval/reject notifications | Backend | 100% | [5 empty] | ◀ | ▶
23 | PR remind button | Full Stack | 100% | [6 empty] | ◆
24 | PO creation notifications | Backend | 100% | [7 empty] | ◆
25 | GRN goods-arrived notifications | Backend | 100% | [7 empty] | ◆
PHASE 6 — Service Centre Module
26 | SRF booking & job card | Full Stack | 100% |  |  | ◀ | ─ | ▶
27 | Technician workbench | Full Stack | 100% |  |  |  |  | ◀ | ▶
28 | Quick bill (walk-in) | Full Stack | 100% | [5 empty] | ◀ | ▶
29 | Store billing & dispatch | Full Stack | 100% | [6 empty] | ◀ | ▶
PHASE 7 — Reporting & Settings
30 | Document templates (GRN/PO/DC) | Frontend | 100% |  |  |  |  | ◀ | ─ | ▶
31 | Tax & HSN settings | Full Stack | 10% |  |  |  | ◀ | ▶
32 | Documentation | Full Stack | 60% | [5 empty] | ◀ | ─ | ─ | ─ | ▶
33 | Dashboard & KPI cards | Frontend | 40% | [8 empty] | ◀ | ▶
34 | Accounts module setup | Full Stack | 0% | [9 empty] | ◀ | ─ | ▶
35 | Reports & exports | Full Stack | 0% | [10 empty] | ◀ | ▶
PHASE 8 — Communication Integrations
36 | WhatsApp Business API integration | Backend | 0% | [9 empty] | ◀ | ─ | ▶
37 | SMS (OTP & alerts) integration | Backend | 0% | [9 empty] | ◀ | ▶
38 | Email (SMTP) integration | Backend | 0% | [9 empty] | ◀ | ▶
39 | Notification preferences UI | Frontend | 0% | [10 empty] | ◀ | ▶
Total Tasks: 39 ¦ Completed: 30 ¦ In Progress: 3 ¦ Planned: 6 ¦ Overall Progress: 77%

## Task Details
ZIMSON SERVICE MANAGEMENT — Task Details
# | Phase | Task / Deliverable | Owner | Start Week | End Week | Duration (Wks) | % Complete | Status | Notes
1 | PHASE 1 — Core System Setup | Project scaffold & DB schema | Full Stack | Week 1 | Week 1 | 1 | 100% | ✅ Completed | Vite + React + Express + PostgreSQL
2 | PHASE 1 — Core System Setup | Authentication & session mgmt | Backend | Week 1 | Week 2 | 2 | 100% | ✅ Completed | Employee code login, JWT sessions
3 | PHASE 1 — Core System Setup | Sidebar & role-based routing | Frontend | Week 1 | Week 2 | 2 | 100% | ✅ Completed | ModuleRoute, AppShell, nav guards
4 | PHASE 1 — Core System Setup | Toast / notification system | Frontend | Week 2 | Week 2 | 1 | 100% | ✅ Completed | Global ToastProvider + useToast
5 | PHASE 2 — Master Data | Region management + PIN lookup | Full Stack | Week 2 | Week 3 | 2 | 100% | ✅ Completed | Address split, postal API, popups
6 | PHASE 2 — Master Data | Store & warehouse management | Full Stack | Week 3 | Week 3 | 1 | 100% | ✅ Completed | Under region hierarchy
7 | PHASE 2 — Master Data | User creation & role system | Full Stack | Week 3 | Week 4 | 2 | 100% | ✅ Completed | Simplified roles, edit/deactivate
8 | PHASE 2 — Master Data | Demo login — DB users | Frontend | Week 4 | Week 4 | 1 | 100% | ✅ Completed | Plain-text password default
9 | PHASE 2 — Master Data | Spares catalogue & bulk import | Full Stack | Week 4 | Week 5 | 2 | 100% | ✅ Completed | Seeded Excel template upload
10 | PHASE 3 — Inventory Procurement | Supplier master + spare mapping | Full Stack | Week 5 | Week 6 | 2 | 100% | ✅ Completed | Supplier form, modal, SparePicker
11 | PHASE 3 — Inventory Procurement | Purchase Request (PR) creation | Full Stack | Week 5 | Week 6 | 2 | 100% | ✅ Completed | Searchable spares, direct to HO
12 | PHASE 3 — Inventory Procurement | PR approval workflow | Full Stack | Week 6 | Week 6 | 1 | 100% | ✅ Completed | HO approval, reject, remind btn
13 | PHASE 3 — Inventory Procurement | PR History page | Frontend | Week 6 | Week 7 | 2 | 100% | ✅ Completed | Status labels, filters, Fulfil
14 | PHASE 3 — Inventory Procurement | Purchase Order (PO) creation | Full Stack | Week 7 | Week 7 | 1 | 100% | ✅ Completed | Consolidated demand → supplier POs
15 | PHASE 3 — Inventory Procurement | PO History page | Frontend | Week 7 | Week 7 | 1 | 100% | ✅ Completed | Stats, search, detail modal, print
16 | PHASE 4 — Goods Receipt & Stock | GRN — cost price & HSN tax | Full Stack | Week 7 | Week 8 | 2 | 100% | ✅ Completed | Auto GST from HSN, CGST/SGST split
17 | PHASE 4 — Goods Receipt & Stock | GRN — vendor invoice upload | Full Stack | Week 8 | Week 8 | 1 | 100% | ✅ Completed | Multer, PDF/image, stored on disk
18 | PHASE 4 — Goods Receipt & Stock | GRN History page | Frontend | Week 8 | Week 8 | 1 | 100% | ✅ Completed | Stats, search, detail modal, print
19 | PHASE 4 — Goods Receipt & Stock | PR auto-status from GRN | Backend | Week 8 | Week 8 | 1 | 100% | ✅ Completed | APPROVED→GOODS_AT_HO on GRN post
20 | PHASE 4 — Goods Receipt & Stock | HO → Store stock fulfil | Full Stack | Week 8 | Week 9 | 2 | 100% | ✅ Completed | Fulfil modal, transfer qty, FULFILLED
21 | PHASE 5 — Notifications & Comms | PR submission notifications | Backend | Week 6 | Week 6 | 1 | 100% | ✅ Completed | HO mgr notified on new PR
22 | PHASE 5 — Notifications & Comms | PR approval/reject notifications | Backend | Week 6 | Week 7 | 2 | 100% | ✅ Completed | Store notified on HO decision
23 | PHASE 5 — Notifications & Comms | PR remind button | Full Stack | Week 7 | Week 7 | 1 | 100% | ✅ Completed | Re-ping HO mgr from store
24 | PHASE 5 — Notifications & Comms | PO creation notifications | Backend | Week 8 | Week 8 | 1 | 100% | ✅ Completed | Store told PO has been raised
25 | PHASE 5 — Notifications & Comms | GRN goods-arrived notifications | Backend | Week 8 | Week 8 | 1 | 100% | ✅ Completed | Store notified goods at HO
26 | PHASE 6 — Service Centre Module | SRF booking & job card | Full Stack | Week 3 | Week 5 | 3 | 100% | ✅ Completed | Watch intake, SRF number, tracking
27 | PHASE 6 — Service Centre Module | Technician workbench | Full Stack | Week 5 | Week 6 | 2 | 100% | ✅ Completed | Job assignment, status updates
28 | PHASE 6 — Service Centre Module | Quick bill (walk-in) | Full Stack | Week 6 | Week 7 | 2 | 100% | ✅ Completed | Invoice, PDF print, history
29 | PHASE 6 — Service Centre Module | Store billing & dispatch | Full Stack | Week 7 | Week 8 | 2 | 100% | ✅ Completed | Billing, DC creation, tracking
30 | PHASE 7 — Reporting & Settings | Document templates (GRN/PO/DC) | Frontend | Week 5 | Week 7 | 3 | 100% | ✅ Completed | Print-ready branded documents
31 | PHASE 7 — Reporting & Settings | Tax & HSN settings | Full Stack | Week 4 | Week 5 | 2 | 10% | 🔄 In Progress | GST rates, invoice config — 10% done
32 | PHASE 7 — Reporting & Settings | Documentation | Full Stack | Week 6 | Week 10 | 5 | 60% | 🔄 In Progress | API docs, user manual — 60% done
33 | PHASE 7 — Reporting & Settings | Dashboard & KPI cards | Frontend | Week 9 | Week 10 | 2 | 40% | 🔄 In Progress | Role-based summary widgets
34 | PHASE 7 — Reporting & Settings | Accounts module setup | Full Stack | Week 10 | Week 12 | 3 | 0% | 📋 Planned | Ledger, P&L, reconciliation — not started
35 | PHASE 7 — Reporting & Settings | Reports & exports | Full Stack | Week 11 | Week 12 | 2 | 0% | 📋 Planned | PR/PO/GRN Excel exports
36 | PHASE 8 — Communication Integrations | WhatsApp Business API integration | Backend | Week 10 | Week 12 | 3 | 0% | 📋 Planned | Order updates, PR alerts via WhatsApp
37 | PHASE 8 — Communication Integrations | SMS (OTP & alerts) integration | Backend | Week 10 | Week 11 | 2 | 0% | 📋 Planned | Twilio / MSG91 — login OTP, status SMS
38 | PHASE 8 — Communication Integrations | Email (SMTP) integration | Backend | Week 10 | Week 11 | 2 | 0% | 📋 Planned | Nodemailer — invoices, approvals, reports
39 | PHASE 8 — Communication Integrations | Notification preferences UI | Frontend | Week 11 | Week 12 | 2 | 0% | 📋 Planned | User-level channel opt-in settings

## Summary
ZIMSON SERVICE MANAGEMENT — Project Summary
| Total Tasks | Completed | In Progress | Planned
| 39 | 30 (77%) | 3 | 6
Phase | Tasks | Done | In Prog | % Complete
Core System Setup | 4 | 4 | 0 | 100%
Master Data | 5 | 5 | 0 | 100%
Inventory Procurement | 6 | 6 | 0 | 100%
Goods Receipt & Stock | 5 | 5 | 0 | 100%
Notifications & Comms | 5 | 5 | 0 | 100%
Service Centre Module | 4 | 4 | 0 | 100%
Reporting & Settings | 6 | 1 | 3 | 17%
Communication Integrations | 4 | 0 | 0 | 0%